## Revision History
Revision History
Date | Revision Number | Changes | Author
2017-12-29 | 1 | Updated for sprint - 1 | Rakesh
2018-01-12 | 1.1 | Updated for sprint - 2 | Rakesh
2018-02-09 | 1.2 | Updated for sprint - 3 | Rakesh
2018-03-02 | 1.3 | Updated for sprint - 4 | Rakesh
2018-03-09 | 1.4 | Updated for sprint - 5 | Rakesh
2018-03-23 | 1.5 | Updated for sprint - 6 | Rakesh
2018-03-23 | 1.6 | Updated for Sprint- 7 | Rakesh
2018-04-06 | 1.7 | Updated for Sprint- 8 | Rakesh

## Metrics
| Sprint 1 | Sprint 2 | Sprint 3 | Sprint 4 | Sprint 5 | Sprint 6 | Sprint 7 | Sprint 8 | Average
Sprint Planned Start Date | 2017-12-18 | 2018-01-01 | 2018-01-29 | 2018-02-12 | 2018-02-26 | 2018-03-12 | 2018-03-12 | 2018-03-26
Sprint Planned End Date | 2017-12-29 | 2018-01-12 | 2018-02-09 | 2018-03-02 | 2018-03-09 | 2018-03-23 | 2018-03-23 | 2018-04-06
Sprint Actual Start Date | 2017-12-18 | 2018-01-01 | 2018-01-29 | 2018-02-12 | 2018-02-26 | 2018-03-12 | 2018-03-12 | 2018-03-26
Sprint Actual End Date | 2017-12-29 | 2018-01-12 | 2018-02-09 | 2018-03-02 | 2018-03-09 | 2018-03-23 | 2018-03-23 | 2018-04-06
Estimated Efforts | 206 | 183 | 160 | 229 | 196 | 218 | 200 | 200
Actual Efforts | 220 | 229 | 179 | 241 | 202 | 214 | 196 | 196
User Story Grooming | 0 | 2 | 2 | 0 | 4 | 4 | 4 | 4
Design | 48 | 22 | 4 | 40 | 14 | 8 | 4 | 4
Coding | 78 | 124 | 101 | 112 | 116 | 122 | 120 | 120
Reviews | 20 | 8 | 6 | 12 | 4 | 4 | 4 | 4
Testing | 40 | 46 | 42 | 49 | 40 | 40 | 40 | 40
Project / Sprint Management | 34 | 27 | 24 | 28 | 24 | 36 | 24 | 24
Velocity | 19 | 20 | 20 | 21 | 17 | 27 | 28 | 53
Number of User Stories Delivered | 5 | 6 | 6 | 6 | 8 | 13 | 8 | 22
Number of User Stories Rejected | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Review Defects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Testing Defects | 2 | 2 | 2 | 2 | 5 | 6 | 3 | 12
Customer Reported Defects | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Metrics
Schedule Deviation | [8 empty] | 0% | bar: 2017-12-29 to 2018-04-06
Effort Deviation | 6.796% | 25.14% | 11.88% | 5.24% | 3.061% | -1.835% | -2% | -2% | 2.39%
Productivity | 11.5789 | 11.45 | 8.95 | 11.4762 | 11.8824 | 7.9259 | 7 | 3.6981 | 8.4888
Defect Density | 0.10526 | 0.1 | 0.1 | 0.095238 | 0.29412 | 0.22222 | 0.10714 | 0.22642 | 0.17419
User Story Rejection | [8 empty] | 0% | bar: 2017-12-29 to 2018-04-06
Velocity | 19 | 20 | 20 | 21 | 23 | 27 | 28 | 53 | 28.6667
Defect Removal Efficiency | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Production Defect Density | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
% Effort Distribution
User Story Grooming | 0% | 0.8734% | 1.117% | 0% | 1.98% | 1.869% | 1.869% | 1.869% | 1.451%
Design | 21.82% | 9.607% | 2.235% |  | 6.931% | 3.738% | 1.869% | 1.869% | 3.328%
Coding | 35.45% | 54.15% | 56.42% | 46.47% | 57.43% | 57.01% | 56.07% | 56.07% | 54.91%
Reviews | 9.091% | 3.493% | 3.352% | 4.979% | 1.98% | 1.869% | 1.869% | 1.869% | 2.653%
Testing | 18.18% | 20.09% | 23.46% | 20.33% | 19.8% | 18.69% | 18.69% | 18.69% | 19.95%
Project/ Sprint Management | 15.45% | 11.79% | 13.41% | 11.62% | 11.88% | 16.82% | 11.21% | 11.21% | 12.69%

## Inferences and actions
Inferences & Actions
Date | Metrics | Actuals | Inferneces / Remarks
2017-12-29 | Schedule Deviation Effort Deviation Productivity Defect Density User Story Rejection Velocity Defect Removal Efficiency Production Defect Density | - the team was able to complete the sprint on time - efforts the team spend 6.80% more efforts than planned - Overal team productivity is 11.58 hours per story point - All the 5 user stories are accepted by the produt owner - Defect density is 0.11 defects / story point - There are no defects observed in production V1.01 release related to these user stories - the velocity of the team is 19 story points | - As this is the first sprint the team got an idea about their performance no actions planned
2018-01-12 | Schedule Deviation Effort Deviation Productivity Defect Density User Story Rejection Velocity Defect Removal Efficiency Production Defect Density | - the team was able to complete the sprint on time - efforts the team spend 25.14% more efforts than planned - Overal team productivity is 11.45 hours per story point - All the 6 user stories are accepted by the produt owner - Defect density is 0.10 defects / story point - There are no defects observed in production V1.01 release related to these user stories - the velocity of the team is 20 story points | - The team spend more time because the tasks were not planned for deployment as there is a release planned after this sprint - There was a change in the deployment environment which took more time - Considering the trend the metrics are almost same as first sprint there is no signficant change observed
2018-02-09 | Schedule Deviation Effort Deviation Productivity Defect Density User Story Rejection Velocity Defect Removal Efficiency Production Defect Density | - the team was able to complete the sprint on time - efforts the team spend 11.88% more efforts than planned - Overal team productivity is 8.95 hours per story point - All the 6 user stories are accepted by the produt owner - defect density is 0.10 defects / story point - There are no defects observed in production V1.02 release related to these user stories - the velocity of the team is 20 story points | - The team spend more time because of the issue observed related to database loading - Considering the trend the metrics are almost same as previous sprint there is no signficant change observed except for productivity
2018-03-02 | Schedule Deviation Effort Deviation Productivity Defect Density User Story Rejection Velocity Defect Removal Efficiency Production Defect Density | - the team was able to complete the sprint on time - efforts the team spend 5.24% more efforts than planned - Overal team productivity is 11.48 hours per story point - All the 6 user stories are accepted by the produt owner - defect density is 0.10 defects / story point - There are no defects observed in production V1.02 release related to these user stories - the velocity of the team is 21 story points | - There are no significant differences observes in the sprint - The sprint went well - This sprint is actually planned for 3 weeks considering the resources availability and the user stories planned to complete the modules it was agreed with the product owner to make this as 3 weeks
2018-03-09 | Schedule Deviation Effort Deviation Productivity Defect Density User Story Rejection Velocity Defect Removal Efficiency Production Defect Density | - the team was able to complete the sprint on time - efforts the team spend 3.06% more efforts than planned - Overal team productivity is 11.88 hours per story point - All the 8 user stories are accepted by the produt owner - defect density is 0.29 defects / story point - There are no defects observed in production V1.03 release related to these user stories - the velocity of the team is 23 story points | - The team is more stabilized with respect to estimations and because of which we observe a decreasing trend in effort variance - The defect density is more as the existing timesheet application has to be replaced - The team had used the pair programming (Partially) to avoid the testing errors
2018-03-23 | Schedule Deviation Effort Deviation Productivity Defect Density User Story Rejection Velocity Defect Removal Efficiency Production Defect Density | - the team was able to complete the sprint on time - efforts the team spend -1.83% more efforts than planned - Overal team productivity is 7.93 hours per story point - All the 8 user stories are accepted by the produt owner - defect density is 0.22 defects / story point - There are no defects observed in production V1.03 release related to these user stories - the velocity of the team is 27 story points | - The effort estimated and spend is adequate and actuals is bit lower than estimated and this is happened because of the resued code which was not considered during the estimations - The team velocity also increased and the team could able to deliver upto 25-28 story points in the last 2 sprints because the team is more stabilized with the application as well as the coordination