## Revision History
Revision History
Date | Revision Number | Changes | Author | Approved By
2017-05-01 | 1 | Initial Document | Sridhar | Anitha T G
Note: The version updated here is the template version, this can be cleared and replaced with the actual version history of the project

## Projects Checklist
Projects Checklist
Evaluation Parameter | Yes/No/NA | Notes
Does the project has a formal agreement between Client and Organization? |  | Statement of Work
Has Delivery Head identified Scrum Master for this project? What was the rationale of choosing the Scrum Master(Adequate Skills and Experience)?
Has the required resources allocated into the project depending upon the skill/technology requirements of the project? |  | Project Management Plan
Was Project Plan prepared for the project? |  | Project Management Plan
Was the Kick off Meeting conducted for the project?
Based upon the final set of requirements was entry of each requirement made in Product Backlog? |  | Project Workbook
Was Priority of requirements set for all the User Stories derived from the Requirements? |  | Project Workbook
Was the backlog capturing Interface related requirements as well? |  | Project Workbook
Was Acceptance Criteria & Story Clarity detailed out for all the User Stories ? |  | Project Workbook
Based upon discussion with client, were distribution of User Stories among Sprints & Releases concluded & detailed out in Product Backlog? |  | Project Workbook
Does the project has detailed sprint plan including the tasks? |  | Sprint Workbook
All the information in the project plan is complete and consistent? |  | Project Management Plan
Did all relevant team members participated in the story point estimation exercise?
Were the estimations reviewed/approved by the Product Owner? |  | Project Workbook
Has the Release planning been done to identify the number number of sprints required for the project ? |  | Project Workbook
Is the “Definition of Done” for release is documented ? |  | Project Workbook
Is the sprint backlog prepared inline with the available hours ? |  | Sprint Workbook
Was sprint Planning Meeting conducted? Did all stakeholders participated in the Sprint Planning meeting?
Does the sprint backlog has the tasks listed, resources associated to the tasks and planned efforts ? |  | Sprint Workbook
Has project documented the project execution Strategy as part of PMP? |  | Project Management Plan
Was revision history of PMP appropriately showcasing modifiations? |  | Project Management Plan
What all Metrics shall be tracked in the project have been clearly mentioned in Project? |  | Project Management Plan
Is Team Structure defined correctly in the PMP? |  | Project Management Plan
Are set of identified Stakeholders defined in PMP? |  | Project Management Plan
Was PMP reviewed and approved by the next level? |  | Project Management Plan
Were all potential risks identified are logged in Risk Tracking Sheet? |  | Risk Tracker
Were daily stand-up meetings being conducted in the project?
Does the development team, scrum master participate in the daily stand up meeting ?
Was Agenda covering following 3 aspects - 1. What did I accomplish yesterday? 2. What will I do today? 3. What obstacles are impeding my progress?
Were routine(weekly/fortnightly/monthly) internal team meetings conducted as per the frequency mentioned in Project Plan?
Were there any MOMs created for the Meetings?
Does the action items came out form the different meetings are tracked and closed? |  | Project Workbook
Were Risk Descriptions, Mitigations and Contingency Actions elaborate and self explanatory? |  | Risk Tracker
Were all Critical Risks discussed during Management Review ? |  | MRM
Do the project implemented mitigation / contingency actions as planned in the risk tracker? |  | Risk Tracker
Do the team attended the required trainings as expected by the project? |  | Project Workbook
Were all dependencies , constraints & impediments identified in the project? |  | Project Workbook
Has the Escalation Channel been defined in PMP? |  | Project Management Plan
Has a Configuration Management Tool been deployed for the project?
Was naming Convention of all documents as mentioned in CM Section of PMP? |  | Project Management Plan
Were Configuration Audits conducted on regular basis?
Were all Approval/Review Emails uploaded in folders?
Was sprint closed on time as per the latest schedule?
IS Weekly Status Report being shared with Client on routine basis?
Are Regular management reviews conducted? |  | MRM
Were Metrics where variation was observed for the month discussed during management reviews? |  | Metrics Analysis Report
Were actions identified from management review are closed? |  | MRM
Wherever required has the project team seeked tailoring approval?
Are the metrics being tracked in the project for each sprint? |  | Metrics Analysis Report
Was Release/Sprint Burn Down Chart being tracked in the project? Was the burndown chart coming appropriately for the sprint? |  | Project Workbook
Were the metrics data sheet discussed as part of sprint retrospection, internal team meeting(s) , Management Reviews? |  | Metrics Analysis Report
Do the project been audited? Report been shared with the project manager?
Any non compliances been addressed adequateliy?
Do the project conducted RCA for any significant deviations observed in the project?
Does the project has Test plan, Test Cases ? |  | Review and Test Report
Do traceability exists between sprint user stories and all other documents/code? |  | Sprint Workbook
Are Coding Guidelines used in the project available with the team? Is the team adhering to the coding guidelines ?
Was peer code review performed in the project? |  | Review and Test Report
Is the build created was appropriately tagged and tested for any integration issues?
Were QA Test Cases written adequately to ensure full coverage ? |  | Review and Test Report
Were Defects logged against failed test cases and tracked till closure? |  | Review and Test Report
Was Release Note evident for the QA Tested code which was delivered to Client ? |  | Release Note
Is demonstration done for the stories developed in the sprint ? Any feedback is been addressed?
Do the project had retrospection done for each sprint? |  | Sprint Workbook
Any issues reported by the customer been addressed adequatly?
Are backup & restoration checks done in the project at regular intervals?

## OPG Checklist (hidden)
QA Checklist
CheckPoints | Yes/No/NA | Notes
Are process inputs used and the correct versions, where applicable?
Contract documentation
Policy
Process and procedures
Were the QA audits adequately planned in the audit calander?
Have QA personnel been assigned to the project and adequately performing their responsibilities?
Have all processes and work products been identified that should be audited by QA?
Have all the process audits been completed per the plan?
Have all the work product audits been completed per the plan?
Have all non-conformances been documented per the documented process and procedures?
Have all non-conformances been adequately dis-positioned and closed?
Are QA records of all audits, non-conformances and other QA activities being maintained?
Have QA personnel been trained in the QA Processes?
Are QA status and metrics being collected, analyzed and reported at the monthly reviews
Are the correct outputs produced?
QA audit reports
Discrepancy reports
QA status and metrics

## Training Checklist (hidden)
Training Checklist
CheckPoints | Yes/No/NA | Notes
Wheter these doucments are available with the training department?
Organizational Training Plan
Training Policy
Process and procedures
List of Trainers
Were the training activities adequately planned in the training Plans?
Have all products, product components, deliverables and work products been identified that should be controlled?
Has all the training planned been scheduled?
Has the training been performed in accordance with the training plans?
Has training attendance been recorded for all training?
Are training courses being evaluated and the results of the evaluations being acted upon?
Have status reports been developed and distributed relative to the training program activities?
Are training records about training being established and maintained?
Does the organization review the status of the strategic training program to ensure that the organization is moving in the appropriate strategic direction?
Have training personnel been trained in the Training related Processes described in the Process Management Handbook?
Are Training status and metrics being collected, analyzed and reported at the monthly reviews
Are the correct outputs produced?
Training Plan
Training schedules
Training Records
Training metrics and reports

## QA Checklist
QA Checklist
CheckPoints | Yes/No/NA | Notes
Are process inputs used and the correct versions, where applicable?
Contract documentation
Policy
Process and procedures
Were the QA audits adequately planned in the audit calander?
Have QA personnel been assigned to the project and adequately performing their responsibilities?
Have all processes and work products been identified that should be audited by QA?
Have all the process audits been completed per the plan?
Have all the work product audits been completed per the plan?
Have all non-conformances been documented per the documented process and procedures?
Have all non-conformances been adequately dis-positioned and closed?
Are QA records of all audits, non-conformances and other QA activities being maintained?
Have QA personnel been trained in the QA Processes?
Are QA status and metrics being collected, analyzed and reported at the monthly reviews
Are the correct outputs produced?
QA audit reports
Discrepancy reports
QA status and metrics

## SAM Checklist (hidden)
SAM Checklist
CheckPoints | Yes/No/NA | Notes
Are process inputs used and the correct versions, where applicable?
Contract documentation
Policy
Process and procedures
Historical data
Project Master Plan (Supplier Section)
Were the Supplier activities adequately planned and documented in the PMP?
Have personnel been assigned to the project and are adequately performing their responsibilities relative to supplier management?
Have all supplier related products, product components, deliverables and work products been identified that should be controlled?
Was there a formal supplier agreement for this product? (PO issued that may include the following addendums: contract, license agreement, SOW, specification, terms and conditions, list of deliverables, schedule, budget, defined acceptance process)
Were appropriate acceptance procedures applied for identifying, tracking, storing and retrieving this product applied?
Were procedures applied to demonstrate acceptability of hardware and software configurations?
If applicable, was the appropriate documentation (e.g., installation, operator's, and user's manuals) provided with this product?
Are appropriate licenses in existence for this product?
Are there appropriate maintenance agreements for this product?
Are there appropriate warranties, ownership and usage rights identified for this product?
If this product was identified as nonconformance, what was done with nonconforming products or materials?
Was the actual cost and schedule (delivered on time) of this product compared with the planned cost and schedule?
Was this product transitioned to the project using the appropriate plans and/or procedure(s)?
Were any risks associated with this product or supplier identified and mitigated?
Was the appropriate supply source utilized?
Have personnel been trained in the Supplier Processes?
Are Supplier status and metrics being collected, analyzed and reported at the monthly reviews
Where there any lessons learned that could improve processes for future products and services?