## Revision History
Revision History
Date | Revision Number | Changes | Author | Approved By
2017-05-01 | 1 | Initial Document | Sridhar | Anitha T G
Note: The version updated here is the template version, this can be cleared and replaced with the actual version history of the project

## Project Checklist
Project Checklist
Audit Report
Project Name | <Name>
Project Manager Name | <Name>
Audit Date | <Date>
Evaluation Parameter | Yes/No/NA | Notes
Does the project has a formal agreement between Client and Organization?
Has Delivery Head identified Scrum Master for this project? What was the rationale of choosing the Scrum Master(Adequate Skills and Experience)?
Has the required resources allocated into the project depending upon the skill/technology requirements of the project?
Was Project Plan prepared for the project?
Was the Kick off Meeting conducted for the project?
Based upon the final set of requirements was entry of each requirement made in Product Backlog?
Was Priority of requirements set for all the User Stories derived from the Requirements?
Was the backlog capturing Interface related requirements as well?
Was Acceptance Criteria & Story Clarity detailed out for all the User Stories ?
Based upon discussion with client, were distribution of User Stories among Sprints & Releases concluded & detailed out in Product Backlog?
Does the project has detailed sprint plan including the tasks?
All the information in the project plan is complete and consistent?
Did all relevant team members participated in the story point estimation exercise?
Were the estimations reviewed/approved by the Product Owner?
Has the Release planning been done to identify the number number of sprints required for the project ?
Is the “Definition of Done” for release is documented ?
Is the sprint backlog prepared inline with the available hours ?
Was sprint Planning Meeting conducted? Did all stakeholders participated in the Sprint Planning meeting?
Does the sprint backlog has the tasks listed, resources associated to the tasks and planned efforts ?
Has project documented the project execution Strategy as part of PMP?
Was revision history of PMP appropriately showcasing modifiations?
What all Metrics shall be tracked in the project have been clearly mentioned in Project?
Is Team Structure defined correctly in the PMP?
Are set of identified Stakeholders defined in PMP?
Was PMP reviewed and approved by the next level?
Were all potential risks identified are logged in Risk Tracking Sheet?
Were daily stand-up meetings being conducted in the project?
Does the development team, scrum master participate in the daily stand up meeting ?
Was Agenda covering following 3 aspects - 1. What did I accomplish yesterday? 2. What will I do today? 3. What obstacles are impeding my progress?
Were routine(weekly/fortnightly/monthly) internal team meetings conducted as per the frequency mentioned in Project Plan?
Were there any MOMs created for the Meetings?
Does the action items came out form the different meetings are tracked and closed?
Were Risk Descriptions, Mitigations and Contingency Actions elaborate and self explanatory?
Were all Critical Risks discussed during Management Review ?
Do the project implemented mitigation / contingency actions as planned in the risk tracker?
Do the team attended the required trainings as expected by the project?
Were all dependencies , constraints & impediments identified in the project?
Has the Escalation Channel been defined in PMP?
Has a Configuration Management Tool been deployed for the project?
Was naming Convention of all documents as mentioned in CM Section of PMP?
Were Configuration Audits conducted on regular basis?
Were all Approval/Review Emails uploaded in folders?
Was sprint closed on time as per the latest schedule?
IS Weekly Status Report being shared with Client on routine basis?
Are Regular management reviews conducted?
Were Metrics where variation was observed for the month discussed during management reviews?
Were actions identified from management review are closed?
Wherever required has the project team seeked tailoring approval?
Are the metrics being tracked in the project for each sprint?
Was Release/Sprint Burn Down Chart being tracked in the project? Was the burndown chart coming appropriately for the sprint?
Were the metrics data sheet discussed as part of sprint retrospection, internal team meeting(s) , Management Reviews?
Do the project been audited? Report been shared with the project manager?
Any non compliances been addressed adequateliy?
Do the project conducted RCA for any significant deviations observed in the project?
Does the project has Test plan, Test Cases ?
Do traceability exists between sprint user stories and all other documents/code?
Are Coding Guidelines used in the project available with the team? Is the team adhering to the coding guidelines ?
Was peer code review performed in the project?
Is the build created was appropriately tagged and tested for any integration issues?
Were QA Test Cases written adequately to ensure full coverage ?
Were Defects logged against failed test cases and tracked till closure?
Was Release Note evident for the QA Tested code which was delivered to Client ?
Is demonstration done for the stories developed in the sprint ? Any feedback is been addressed?
Do the project had retrospection done for each sprint?
Any issues reported by the customer been addressed adequatly?
Are backup & restoration checks done in the project at regular intervals?

## Audit Result
Audit Result
# | Audit Result | Category (NC/Observation) | Actions identified | Owner | Closed Date | Status | Remarks